## Sheet1
Big Data Analytics Project Task List
Project Name: | Predicting Crime Rates using Taxi rides data
Team Members: | 1) Carlos Petricioli (cpa253)
2) Valerie Angulo (vaa238)
3) Varsha Muralidharan (vm1370)
Task | Who | Start Date | End Date | Comments
Data Planning Stage
Identify data sources | All | Oct 23 | Oct 24
Plan where data will reside | All | Oct 24 | Oct 27 | • We will initialy have about 250GB of data
• We will save it on Dumbo
Taxi Rides Processing
Write code to ingest data source 1 | Carlos | Oct 27 | Oct 31 | •In this step, you'll read the data from the source and write it or copy it into HDFS
Write code to profile data source 1 | Varsha | Nov 2 | Nov 9 | •This is to characterize the data and the range of values in each column
•You might notice unexpected values in a column - you may decide to normalize the values (e.g. Street vs. St. vs. street) in the ETL stage
•Find min, max, and averages
•Find min and max length of text fields
Write code to clean/format (ETL) data source 1 | Valerie | Nov 2 | Nov 9
NYPD Crimes Processing
Write code to ingest data source 2 | Carlos | Oct 27 | Oct 31 | •In this step, you'll read the data from the source and write it or copy it into HDFS
Write code to profile data source 2 | Varsha | Nov 2 | Nov 9 | •This is to characterize the data and the range of values in each column
•You might notice unexpected values in a column - you may decide to normalize the values (e.g. Street vs. St. vs. street) in the ETL stage
•Find min, max, and averages
•Find min and max length of text fields
Write code to clean/format (ETL) data source 2 | Valerie | Nov 2 | Nov 11
Weather data Processing
Write code to ingest data source 3 | Carlos | Oct 27 | Oct 31 | •In this step, you'll read the data from the source and write it or copy it into HDFS
Write code to profile data source 3 | Varsha | Nov 2 | Nov 9 | •This is to characterize the data and the range of values in each column
•You might notice unexpected values in a column - you may decide to normalize the values (e.g. Street vs. St. vs. street) in the ETL stage
•Find min, max, and averages
•Find min and max length of text fields
Write code to clean/format (ETL) data source 3 | Valerie | Nov 2 | Nov 11
Develop, Test, and Refine the Analytic
Design the analytic(s) | All | Oct 23 | Nov 2 | Based on our model
Code the analytic(s) | All | Nov 11 | Nov 21 | To try to relate crime, weather and taxi data
Test the analytic(s) | All | Nov 21 | Nov 25 | To see what patterns we get
Analyze results of analytic(s) | All | Nov 25 | Dec 3 | •Are the results what you expected?
| All | Nov 25 | Dec 3 | •Do you need to adjust the analytic(s)?
Iterate on the analytic | All | Dec 3 | Dec 10 | •To improve results, and/or to better understand results
Final analytic code due | All | - | 2017-12-15