## Sheet1
Big Data Analytics Project Task List
Project Name: | Predicting Crime Rates using Taxi rides data
Team Members: | 1) Carlos Petricioli (cpa253)
2) Valerie Angulo (vaa238)
3) Varsha Muralidharan (vm1370)
Task | Who | Start Date | End Date | Comments
Data Planning Stage
Identify data sources | All | oct/23 | oct/24
Plan where data will reside | All | oct/24 | oct/27 | • We will initialy have about 250GB of data
• We will save it on Dumbo
Taxi Rides Processing
Write code to ingest data source 1 | Carlos | oct/27 | oct/31 | •In this step, you'll read the data from the source and write it or copy it into HDFS
Write code to profile data source 1 | ? | ? | ? | •This is to characterize the data and the range of values in each column
•You might notice unexpected values in a column - you may decide to normalize the values (e.g. Street vs. St. vs. street) in the ETL stage
•Find min, max, and averages
•Find min and max length of text fields
Write code to clean/format (ETL) data source 1 | ? | ? | ?
NYPD Crimes Processing
Write code to ingest data source 2 | Carlos | oct/27 | oct/31 | •In this step, you'll read the data from the source and write it or copy it into HDFS
Write code to profile data source 2 | ? | ? | ? | •This is to characterize the data and the range of values in each column
•You might notice unexpected values in a column - you may decide to normalize the values (e.g. Street vs. St. vs. street) in the ETL stage
•Find min, max, and averages
•Find min and max length of text fields
Write code to clean/format (ETL) data source 2 | ? | ? | ?
Weather data Processing
Write code to ingest data source 3 | Carlos | oct/27 | oct/31 | •In this step, you'll read the data from the source and write it or copy it into HDFS
Write code to profile data source 3 | ? | ? | ? | •This is to characterize the data and the range of values in each column
•You might notice unexpected values in a column - you may decide to normalize the values (e.g. Street vs. St. vs. street) in the ETL stage
•Find min, max, and averages
•Find min and max length of text fields
Write code to clean/format (ETL) data source 3 | ? | ? | ?
Develop, Test, and Refine the Analytic
Design the analytic(s) | All | oct/23 | ?
Code the analytic(s) | All | ? | ?
Test the analytic(s) | All | ? | ?
Analyze results of analytic(s) | All | ? | ? | •Are the results what you expected?
| All | ? | ? | •Do you need to adjust the analytic(s)?
Iterate on the analytic | All | ? | ? | •To improve results, and/or to better understand results
Final analytic code due | All | -